## How to use
Risk register template
From risksamurai.com — free to use and adapt. Guide: https://risksamurai.com/guides/risk-register-template
1. Agree your scales on the Scales sheet before scoring anything. Replace the example £ thresholds with numbers that fit your organisation.
2. Write each risk as cause → event → consequence in columns C–E. The four example rows show the style; delete them when you start.
3. Score inherent likelihood and impact (columns H–I) as if no controls existed. Score and level calculate automatically.
4. List only controls that operate today (column L), then score residual likelihood and impact (M–N).
5. Choose a response: Treat, Tolerate, Transfer or Terminate. Every Treat needs an action, an owner and a due date.
6. Set a target score and the next review date. Review critical and significant risks monthly, the full register at least quarterly.
Outgrowing the spreadsheet? Risk Samurai imports this file, keeps the history of every change and reminds owners before deadlines: https://risksamurai.com

## Risk register
ID | Risk title | Cause | Event | Consequence | Category | Owner | Inherent likelihood (1-5) | Inherent impact (1-5) | Inherent score | Inherent level | Existing controls | Residual likelihood (1-5) | Residual impact (1-5) | Residual score | Residual level | Response | Actions | Action owner | Due date | Target score | Status | Last reviewed | Next review
R-01 | Payment provider outage | Single payment provider for all online sales | Provider outage or account freeze | All sales stop; c. £18k lost per day of peak trading | Operational | COO | 4 | 5 |  |  | Provider SLA; status-page alerts | 3 | 5 |  |  | Treat | Onboard backup payment provider | COO | 2027-01-31 | 8 | In treatment | 2026-10-01 | 2026-11-01
R-02 | Ransomware attack | Phishing and unpatched systems | Ransomware encrypts order and stock systems | Several days of lost trading; recovery costs; data exposure | Technology | Head of IT | 3 | 5 |  |  | MFA; daily off-site backups; EDR | 2 | 5 |  |  | Treat | Quarterly full restore test | Head of IT | 2026-12-15 | 5 | In treatment | 2026-10-01 | 2026-11-01
R-03 | Key supplier disruption | Top 20 lines sourced from one country | Supplier cannot ship for 4+ weeks | Stock-outs on best sellers; lost revenue | Supply chain | Buying lead | 3 | 4 |  |  | 6 weeks of safety stock on top 20 lines | 2 | 4 |  |  | Tolerate | Review stock cover monthly | Buying lead |  | 8 | Monitoring | 2026-10-01 | 2027-01-01
R-04 | Key person dependency | Supplier terms and pricing known only to the founder | Founder unavailable for an extended period | Unable to negotiate or reorder; margin loss | People | CEO | 3 | 4 |  |  | None | 3 | 4 |  |  | Treat | Document supplier terms; add second signatory | CEO | 2026-12-31 | 6 | Open | 2026-10-01 | 2026-11-01

## Scales
Likelihood
Score | Label | Guide (adapt to your organisation)
1 | Rare | Less than 5% chance in the next 12 months
2 | Unlikely | 5–20%
3 | Possible | 20–50%
4 | Likely | 50–80%
5 | Almost certain | More than 80%
Impact
Score | Label | Financial (example) | Operations (example) | Reputation / compliance (example)
1 | Minor | < £10k | Disruption under 1 hour | No external attention
2 | Moderate | £10k–£50k | Up to 1 day | Customer complaints
3 | Significant | £50k–£250k | Up to 1 week | Local media; regulator enquiry
4 | Major | £250k–£1m | Up to 1 month | National media; formal investigation
5 | Severe | > £1m | More than 1 month | Fine, licence at risk, loss of key customers
Risk levels: 1–4 Low · 5–9 Moderate · 10–14 Significant · 15–25 Critical

## Matrix
5×5 risk matrix (likelihood × impact)
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5